## Slide 1: Project Management
Module 7
Part 2

## Slide 2: Example of Cost Slope
CS = CC – NC = $900 - $500 = $200/day
NT – CT 7 - 5

## Slide 3: Cost-Time Trade-Off Procedure
Collect normal and crash times and costs for all activities in the project planning network.
Compute the total direct costs at normal time.
Compute the cost slope for each activity and find the maximum units of time each activity can be crashed.

## Slide 4: Continued
Construct a total direct cost curve over a range of project durations- or until reduction of critical activities is impossible.
Collect the total indirect costs over the same range of project durations.
Compute the optimum cost-time schedule.
7. Compare the optimum cost-time schedule with any alternative schedule that may be under consideration.

## Slide 5
Collect normal and crash times and costs for all activities in the project planning network.

## Slide 6
Normal And Crash Costs
(Thousands of Dollars)
Activity Normal Time Normal Crash Crash Cost Maximum
(Weeks) Direct Time Direct Slope Improvement
Costs Cost
1-2 4 $5 3 $12 $7 1
1-3 5 $9 3 $19 $5 2
1-4 8 $11 5 $41 $10 3
2-3 2 $20 2 $20 0 0
2-4 4 $8 3 $18 $10 1
3-5 9 $14 5 $58 $11 4
4-5 4 $9 3 $18 $9 1

## Slide 7
1
2
4
3
5
15 Week Schedule
Normal Time: 15 weeks
Normal Cost: $76,000
5
4
8
2x
4
4
9

## Slide 8
1
2
4
3
5
5
3x
8
2x
4
4
9
14 Week Schedule
Total Direct Cost: 76 + 7 = 83
Activity Changed: 1-2 Cost $7

## Slide 9
1
2
4
3
5
5
3x
8
2x
4
4
8
13 Week Schedule
Total Direct Cost: 83 + 11 = 94
Activity Changed: 3-5 Cost $11

## Slide 10
1
2
4
3
5
5
3x
8
2x
4
4
7
12 Week Schedule
Total Direct Cost: 94 + 11 = $105
Activity Changed: 3-5 Cost $11

## Slide 11
1
2
4
3
5
5
4
8
2x
4
3x
6
11 Week Schedule
Total Direct Cost: 105 + 11 + 9 = $125
Activities Changed: 3-5 Cost $11
4-5 Cost $9

## Slide 12
1
2
4
3
5
5
3x
7
2x
4
3x
5x
10 Week Schedule
Total Direct Cost: 125 + 11 + 10 = $146
Activities Changed: 3-5 Cost $11
1-4 Cost $10

## Slide 13: Project Total-Cost Table and Graph
Project Duration 10 11 12 13 14 15
Direct Costs 146 125 105 94 83 76
Indirect Costs 70 74 79 85 100 116
Total Costs 216 199 184 179 183 192

## Slide 14
13
14
15
12
10
11
240
220
200
180
160
140
120
100
80
Total Costs
Indirect Costs
Direct Costs

## Slide 15: Low Cost Schedule with Incentive
Project Duration 10 11 12 13 14 15
Total Cost 216 199 184 179 183 192
Less Incentive
Saving 0 30 24 18 12 6
Resultant Cost 186 175 166 167 177 192

## Slide 16: Questions?